## Sheet1
COMP 4910/4920 Project Effort Log, Project Code: O2T, 20.10.2023, v1.0
Week | Dates | Emre Görkem AĞKURT |  | Ugur BULAN |  | Total Weekly Effort in Man-Hours
|  | Work Done | Total Hours Spent | Work Done | Total Hours Spent
Week 1 | 2022-02-01 | R&D Hardware | 18 | R&D software | 20 | 38
Week 2 | 2022-02-08 | R&D raspberry | 16 | R&D Java | 18 | 34
Week 3 | 2022-02-15 | R&D arduino | 14 | R&D kotlin | 16 | 30
Week 4 | 2022-02-22 | R&D components | 12 | R&D Android std. | 14 | 26
Week 5 | 03/01/2022 | rsd report1.0 | 10 | rsd 1.0 | 12 | 22
Week 6 | 2022-03-08 | dsd report 1.0 | 14 | dsd report1.0 | 16 | 30
Week 7 | 2022-03-15 | final report 1.0 | 12 | final report 1.0 | 14 | 26
Week 8 | 2022-03-22 | hardware power RD | 10 | software demo | 12 | 22
Week 9 | 2022-03-29 | alternative hw test | 8 | software demo | 10 | 18
Week 10 | 2022-04-05 | re R&D hardware | 10 | mobile app demo | 8 | 18
Week 11 | 2022-04-12 | Meeting | 8 | Meeting | 8 | 16
Week 12 | 2022-04-19 | software imp. | 10 | software imp. | 12 | 22
Week 13 | 2022-04-26 | alternative hw search | 12 | circuit design | 12 | 24
Week 14 | 2023-01-29 | rsd report2.0 | 14 | circuit design | 10 | 24
Week 15 | 2023-02-19 | dsd report 2.0 | 10 | circuit design | 4 | 14
Week 17 | 2023-02-26 | final report 2.0 | 8 | final report 2.0 | 5 | 13
Week 18 | 03/05/2023 | demo testing | 12 | demo testing | 8 | 20
Total Effort in Man-Hours |  |  | 198 |  | 199 | 397
Total Effort in Man-Days |  |  | 24.75 |  | 24.875 | 49.625
Notes:
1. This table shows the consolidated project effort, based on project effort tables prepared by each team member 2. Replace Team Member i with team member name and lastname, then fill out one column for each team member
Form: O2T-Project Effort Log-2020-10-20-v1.0.xlsx